## How to use this document
Example RACI Template
HOW TO USE THIS DOCUMENT
The responsible, accountable, consulted, and informed (RACI) documents for operations and marketing are intended to help you build clarity and accountability with your stakeholders.
We have listed several common tasks in each RACI and have organized them by pre-launch, launch, and post-launch to help compartmentalize the concepts and get you started.
There is no limit to the number of tasks that you can have in a given section; the key is being deliberate and very specific in each task so that there is maximum clarity.
Create the list of tasks with your stakeholder (or use AI to help you accelerate the creation of the task list), and agree upon the RACI assignments.

## Marketing RACI
Example RACI Template
TASKS | MARKETING |  |  | ENABLEMENT/FIELD ACTIVATION |  |  | RESPONSIBLE | ACCOUNTABLE | CONSULTED | INFORMED
| Content Marketing | Segment Leader | Vice President | Communication and Events | Activation Director | Vice President | R | A | C | I
Pre-Launch
Create pitch deck.
Create pitch talk track.
Create demo.
Create client brochure (find existing or create new).
Create competitive positioning (find existing or create new).
Create customer stories (find existing or create new).
Launch
Send invites to sessions.
Align with Field Enablement team.
Put event in enablement calendar.
Conduct enablement live session.
Deliver enablement lessons and certifications.
Create field play.
Post-Launch
Pull together Enablement Analytics Report.
Review Enablement Analytics Report.
Partner with operations to evolve reporting/ Salesforce (or other tech) systems based on feedback from field play contributors and stakeholders.
Collect and summarize field feedback so it can be actioned by play contributors/stakeholders.
Create action plan around feedback.
Iterate on content.

## Ops RACI
Example RACI Template
TASKS | ENABLEMENT |  | COMMERCIAL OPERATIONS |  |  |  |  | RESPONSIBLE | ACCOUNTABLE | CONSULTED | INFORMED
| Field Enablement | Field Activation | Sales Operations | Services Operations | Proposal Management | Customer Success Operations | Partner Operations | R | A | C | I
Pre-Launch
Determine metrics of success for tool adoption.
Gain awareness of changes in pricing and packaging.
Communicate changes in tech stack to enablement.
Build project plan.
Define customer relationship management (CRM) needs.
Launch
Launch the enablement (TIER 1).
Launch the enablement (TIER 2).
Launch the enablement (TIER 3).
Launch the enablement (TIER 4).
Publish content to correct profiles.
Post-Launch
Communicate information to onboarding team.
Take 30-day snapshot.
Take 60-day snapshot.
Take 90-day snapshot.
Communicate tech stack changes/updates.
Update documentation.
Operations Council
Bring data, observations, recommendations.
Surface current content for review.
Review current content for changes.

## Charter Roadshow (hidden)
CHARTER ROADSHOW
| Cadence | Day | Audience | Q1 date | Owner
SDR | Weekly |  | Leadership
SDR | TBD |  | All Hands
SE | Bi-weekly | Monday | Leadership
SE | Quarterly | Week 2 at top of quarter | All Hands
VE | Bi-weekly | Thursday | All Hands
AMs | Bi-weekly | Monday at 2PM ET | All Hands
CSMs | Monthly | First Friday | All Hands
GS | Quarterly |  | All Hands | 2023-02-23
CEX | Weekly | Mondays at 2PM ET | All Hands
Commercial Sales | Weekly | Monday | Leadership
Commercial Sales | Bi-Weekly | Tuesday | All Hands
CEMEA (all GTM) | Bi-Quarterly |  | All Hands |  |  | **First Friday also includes AMs, CEX, and GS so could do one call to catch all groups!
FR | Weekly | Monday | All Hands
APAC | Quarterly |  | All Hands | 2023-02-01
Global Partnerships | Weekly | Tuesday | All Hands | 2023-02-07 | Amanda